K2 FITNESS MANIACS · MENEOU, LARNACA

What's left before this takes real money

An audit of the build as it stands — run against the working tree, not from memory. Split into three gates. Gate 1 is genuinely blocking: skip any of it and you either cannot take an order, or should not.

Every item is marked You, Dev, or Both. Of the ten blocking items, seven are yours and only three are code — the constraint is not development, it is accounts, legal text and content.

AT A GLANCE

- Gate 1 — 10 items. Blocking. No real orders until all ten are done.

- Gate 2 — 6 items. These break, embarrass, or cost money within month one.

- Gate 3 — 6 items. Growth work, deliberately after launch.

Start 1.1 today. Merchant approval is an underwriting decision on Viva’s side, so it takes days, and six other items queue behind it. Everything else in Gate 1 can happen while you wait.

GATE 1

# Blocking — no real orders until all ten are done

Two kinds of blocker are mixed here on purpose: things that make the shop technically unable to take a payment, and things that make it unlawful or dishonest to take one. They gate the launch equally.

1.1  Get the Viva.com merchant account approved    YOU   days of waiting

Apply at viva.com as the business. They will want company registration documents, ID for the directors, and the payout bank account. This is an underwriting decision on their side, so it is not same-day — which is exactly why it goes first. Nothing else in Gate 1 can be finished until it clears.

1.2  Wire the live credentials and the return URLs    YOU   ~20 min

Live Smart Checkout credentials into the Vercel environment variables, then create the Website payment source and set its Success and Failure URLs to https://your-domain/api/return.

Get those URLs wrong and customers pay, then land on a blank page — it is the most common failure in this whole integration. Exact click-path is in PAYMENTS.md. Keep VIVA_ENV=demo everywhere until the rest of this gate is closed.

1.3  Write the terms, returns and privacy policies    YOU   a week, mostly waiting

The footer links are placeholders pointing at the contact page. Selling to consumers in Cyprus needs real terms of sale, a returns and refund policy, a privacy notice, and — once you add analytics — a cookie notice. The returns policy has to reflect the 14-day right of withdrawal EU consumers have on distance sales.

A template beats nothing, a lawyer beats a template, and this is the item people put off until the week they launch.

1.4  Put the company and VAT numbers in the footer    YOU   10 min

Registered company name, registration number, VAT number, trading address. An EU online trader is required to show these, and their absence is the first thing a suspicious customer notices. Send them over or edit src/lib/shop.js.

1.5  Confirm the VAT rate with his accountant    YOU   one phone call

The code assumes 19% standard, VAT-inclusive pricing and extracts VAT out of the displayed total. Whether food supplements sit at the standard rate or a reduced one depends on how each product is classified — a question for his accountant, not for a developer. If the answer differs it is one constant in src/lib/pricing.js and everything downstream follows.

1.6  Deploy to Vercel on the real domain    BOTH   ~1 hour

Push to GitHub, import the repo into Vercel, add the environment variables, point the .com.cy DNS at it.

Note Vercel's free Hobby tier is for non-commercial projects — check their current terms and budget for the paid tier, since a shop taking money is commercial use.

1.7  Attach durable order storage    YOU   5 min

Vercel → Storage → Upstash Redis. It sets the two variables the code already looks for, so there is no code change.

Skip it and orders live in the memory of a serverless instance: the payment is still safe at Viva, but a customer who just paid can hit a "no such order" page. Cheapest fix on this entire list.

1.8  Turn on order emails and verify the sending domain    YOU   ~30 min

Card customers get a receipt from Viva automatically. For cash-on-delivery and reserve-in-shop, the email to the shop is the only thing that tells anyone an order exists — without it those orders are invisible and the customer waits for a box nobody packed.

Create a Resend account, verify the domain (unverified senders go to spam), set RESEND_API_KEY and SHOP_ORDER_EMAIL.

1.9  Replace the #/ routes with real URLs    DEV   2–3 hours

Today a product lives at /#/product/asl-isolate-90. Everything after the # is invisible to a server, so search engines cannot treat product pages as separate pages and none of them can rank — fatal for a shop that wants to be found for "whey protein Larnaca".

HashRouter was chosen so the demo runs by double-clicking a file; that trade-off stops making sense the moment it is hosted. Needs BrowserRouter plus a rewrite rule in vercel.json, which is not there yet — without it, refreshing any deep link 404s.

1.10  Make the contact and newsletter forms actually send    DEV   ~2 hours

Both currently say "Thanks — we will reply today" and then throw the message away. It was honest in a demo and it is indefensible on a live site: a customer asks a question, believes it was sent, and never hears back. Needs a real endpoint behind each, reusing the mail setup from 1.8.

GATE 2

# Month one — these break, embarrass, or cost him money

You could launch without these. You will regret each one within about four weeks of real traffic, and he will ask about them in roughly this order.

2.1  Load the real catalogue    BOTH   depends on his data

There are 33 demo products against his 600-plus real ones, and only seven prices are genuinely his. Get his product list out of whatever he uses now — a spreadsheet export is ideal, even a messy one — and the importer can be written around it. Until this is done the site cannot go live in any honest form.

2.2  Get product photography    YOU   a day of shooting

Every product is currently a drawn SVG tub. It looks deliberate rather than broken, which is why the demo holds up, but it is the biggest visual gap between this and a real shop.

Two routes: shoot the shelves in the shop on a phone against a plain backdrop, or ask each importer for their brand asset packs — most hand them over free. The code already renders a photo the moment a product has an image field.

2.3  Build real stock control    BOTH   1–2 days + a decision

Stock is a hard-coded number in a file today and nothing decrements it. Two customers can buy the last tub in the same minute and both get charged. It also means the shop floor and the website drift apart immediately.

Needs the catalogue in a database with stock decremented inside the payment flow — so it needs a decision from you on where that database lives.

2.4  Build an admin screen for orders    DEV   1–2 days

Orders arrive as email and that is the entire workflow — no way to see today’s list, mark one packed or shipped, or look up what a customer ordered last month. Workable for the first week at low volume, painful by the second.

2.5  Fix search for Greek    DEV   ~1 hour

A real bug found while auditing: search matches product names and the English descriptions only. Flip the site to Ελληνικά, search "πρωτεΐνη", and you get nothing back — on a bilingual shop in Cyprus that is half the audience hitting an empty results page. Also wants accent-insensitive matching, since people type without accents.

2.6  Add the SEO basics    DEV   half a day

There is one title tag for the whole site, no per-page descriptions, no Open Graph tags, no sitemap.xml, no robots.txt, and no Product structured data. So every page shares one Google result, and a link shared on WhatsApp or Instagram shows no preview card.

Only worth doing after 1.9 — real URLs are the foundation the rest sits on.

GATE 3

# After launch — growth, once it's live and steady

Deliberately not before launch. Each is easier to justify, and to spec, once there is real traffic to look at.

3.1  Analytics, and the cookie banner it forces    BOTH   half a day

Worth noting the order of causation: the site currently sets no tracking cookies at all, so it needs no consent banner. Add Google Analytics and you inherit the consent requirement. A cookieless option like Plausible avoids the banner entirely — weigh that before defaulting to GA.

3.2  Courier integration and label printing    BOTH   1–2 days

Whoever he ships with — ACS, Cyprus Post, a local courier — most have an API for creating consignments and printing labels. Turns packing from retyping addresses into pressing a button, and gives the customer a tracking number.

3.3  Customer accounts and order history    DEV   2–3 days

His current site has these, so expect him to raise it — worth saying out loud in the meeting that it is a deliberate phase-two cut, not an oversight. Repeat buyers reordering the same tub is the actual value; "reorder my last one" is the feature that earns its keep.

3.4  Discount codes and abandoned-cart email    DEV   2 days

The two highest-return additions once traffic exists. Discount codes let him run the Instagram promotions he already runs; abandoned-cart recovery typically pays for itself faster than anything else on this list.

3.5  Invoices and an accounting export    BOTH   1–2 days

Sequential invoice numbering, a PDF per order, and an export his bookkeeper can actually use. Ask the accountant what format they want before building it — guessing here means doing it twice.

3.6  Google and Meta shopping feeds    DEV   1 day

A product feed puts the catalogue into Google Shopping and Instagram tagging. Needs 2.1 and 2.2 finished first — a feed of drawn placeholder tubs is worse than no feed.

DONE

# Already built and tested

So the list above reads in proportion. All of this works now, and 46 automated checks cover the payment paths (npm run test:checkout).

- Card checkout via Viva Smart Checkout, sandbox-verified

- Apple Pay and Google Pay on supported devices

- Cash on delivery, no payment provider needed

- Reserve online, pay at the counter

- Pay online, collect in Meneou

- Server-side pricing — a tampered price is ignored

- Payment verified against Viva's API, never the browser

- Forged webhooks cannot mark an order paid

- Amount mismatches held for review, not fulfilled

- Webhook catches customers who close the tab after paying

- Free-delivery threshold and cash-on-delivery surcharge

- VAT extracted correctly from inclusive prices

- Order status pages for every outcome

- Full English / Greek toggle on every string

- Shop with filters, sorting and shareable URLs

- Bundle stacks that add three items at once

- Mobile layouts down to 390px

- Sandbox mode fails safe — cannot charge by accident

# What it costs to run

Confirm every figure directly with the provider. Pricing and tier terms change, and Cyprus card rates in particular are negotiated per merchant.

| SERVICE | WHAT FOR | ROUGH EXPECTATION |
| --- | --- | --- |
| Viva.com | Card processing | Per-transaction fee, plus a possible monthly minimum. Ask for a written quote for a Cyprus retail merchant — do not rely on a published headline rate. |
| Vercel | Hosting and the API | Free Hobby tier excludes commercial use, so budget for the paid tier. Check current terms. |
| Upstash Redis | Order storage | Free tier is generous well past this shop's volume. |
| Resend | Order emails | Free tier covers a few thousand emails a month. |
| Domain | fitnessmaniacs.com.cy | He already owns it — it just needs the DNS pointed. |

One thing worth pricing separately: whoever writes the terms, returns and privacy policies (1.3). It is the only item here that usually needs paying a professional, and the one most often left to the last week.

Payment specifics are in PAYMENTS.md. Pitch notes in README.md. This document mirrors LAUNCH.md in the project.